## Sheet1
Task ID | PB Items | Task Description | Assigned To | Not Started | In Progress | Completed | Definition of Done | Notes
T1 | PB1 | Update scheduler logic for numberOfGames per league | Bashar Al Jashmi | 2024-12-01 | 2024-12-01 | 2024-12-03 | DoD: Code updated to limit games per numberOfGames. All baseline tests (cases 1–4) pass without errors. | Re-ran initial tests on Dec 3, resolved minor logic issues before completion.
T2 | PB2 | Write unit tests for interval overlaps & venue availability | Mohammad Al Nadaf | 2024-12-01 | 2024-12-02 | 2024-12-05 | DoD: New tests run successfully, coverage ≥90%, no interval overlap issues remain. | Found a coverage gap on Dec 4, fixed by Dec 5.
T3 | PB1 | Update CSV (cases 5–8) & adjust test asserts for numberOfGames | Bashar Al Jashmi | 2024-12-01 | 2024-12-03 | 2024-12-07 | DoD: CSV changes applied, test thresholds updated, cases 5–8 tests all pass. | Delayed for PO feedback (Dec 4–5), finished after retesting on Dec 7.
T4 | PB1, PB2 | Create documentation (End-to-End scenario, test cases doc, sprint notes) | Mohammad Al Nadaf | 2024-12-01 | 2024-12-06 | 2024-12-09 | DoD: Docs reviewed, meet requirements, approved by team. | Started docs after tests stabilized on Dec 6; completed Dec 9 after review.
T5 | PB1, PB2 | Product Backlog refinement post-review | Sharmarke Ismael (PO) | 2024-12-01 | 2024-12-09 | 2024-12-10 | DoD: Backlog updated post Sprint Review, clarity for next iteration. | Minimal effort after Sprint Review on Dec 9, done by Dec 10.
T6 | Process (N/A) | Facilitate daily scrums, remove impediments, ensure SCRUM adherence | Abdullahi Nor (SM) | 2024-12-01 | Dec 1–11 | 2024-12-11 | DoD: ≥3 daily scrums held, impediments addressed, all sprint ceremonies followed, PO satisfied with process outcome. | Ongoing throughout sprint, completed at end (Dec 11).
T7 | PB1, PB2 | Verify Case 1 scenario (8 Teams, 1 League, uniform availability) | Bashar Al Jashmi | 2024-12-01 | 2024-12-03 | 2024-12-04 | DoD: Case 1 schedule respects numberOfGames, no overlaps, tests pass. | Began after T1 done, quick check, completed by Dec 4.
T8 | PB1, PB2 | Verify Case 2 scenario (8 Teams, 3 Leagues, uniform availability) | Bashar Al Jashmi | 2024-12-01 | 2024-12-04 | 2024-12-06 | DoD: All 3 leagues follow numberOfGames, no overlaps, tests adjusted & pass. | Needed extra half-day due to multiple leagues, done Dec 6.
T9 | PB1, PB2 | Verify Case 3 scenario (16 Teams, 1 League, 1 field) | Bashar Al Jashmi | 2024-12-01 | 2024-12-06 | 2024-12-07 | DoD: Single-field scenario checked, numberOfGames upheld, no overlaps. Tests pass. | Started after CSV stable; simpler scenario, done by Dec 7.
T10 | PB1, PB2 | Verify Case 4 scenario (24 Teams, limited availability) | Bashar Al Jashmi | 2024-12-01 | 2024-12-07 | 2024-12-08 | DoD: Adjusted numberOfGames for limited weeks, verified no overlaps, tests pass. | Careful scheduling due to limited weeks; done Dec 8.
T11 | PB1, PB2 | Verify Case 5 scenario (52 teams, 3 leagues, limited venues) | Bashar (main), Mohammad (assist) | 2024-12-01 | 2024-12-08 | 2024-12-10 | DoD: Complex data; numberOfGames triple-checked, no overlaps, tests stable. | Data mismatch on Dec 9 fixed by Mohammad; completed Dec 10.
T12 | PB1, PB2 | Verify Case 6 scenario (104 teams, 3 leagues, limited venues) | Bashar Al Jashmi | 2024-12-01 | 2024-12-09 | 2024-12-10 | DoD: Large-scale test done, numberOfGames logic holds, no overlaps, tests pass. | Started after Case 5 done, finished Dec 10.
T13 | PB1, PB2 | Verify Case 7 scenario (104 teams, varied games, limited venues) | Bashar Al Jashmi | 2024-12-01 | 2024-12-10 | 2024-12-10 | DoD: Complex scenario handled; no overlaps; numberOfGames balanced, tests pass. | Leveraged previous large tests; done same day (Dec 10 PM).
T14 | PB1, PB2 | Verify Case 8 scenario (104 teams, full availability) | Bashar Al Jashmi | 2024-12-01 | 2024-12-10 | 2024-12-11 | DoD: Full availability simpler; no exceed numberOfGames, no overlaps, tests pass. | Quick overnight check; done by Dec 11 morning.
T15 | PB1, PB2 | Verify Generated case (large random data, some errors) | Bashar Al Jashmi | 2024-12-01 | 2024-12-11 | 2024-12-11 | DoD: Handles erroneous data gracefully, defaults if invalid numberOfGames; no overlaps, tests pass. | Final test last day; minor trial & error, done by noon Dec 11.